 Upgrading System ISO 9001:2008 to ISO 9001:2015

Draft updated date: 02/02/16
Scope

The purpose of this document is to create a check list of work that need to be performed to bring the ISO system being run by Viamed VST and (to a limited degree) Vandagraph to the Newer ISO 9001:2015 standards.

# THIS IS A WORK IN PROGRESS DOCUMENT.

Preamble.

ISO 9001 has been overhauled, the current Viamed system appears to cover most newer requirements of the standards.
ISO 13485 has also now been released in draft form. Any changes to the system should take into consideration the newer upcoming 13485 standard.
The Most fundamental change to ISO appears it is no longer 'product' or 'service' based but analyses the entire organisation as inputs – Processes – outputs.
The new standard puts emphasis on Risk managment of each process.

Going forward. The whole of the current ISO system now requires a review / updating.

The following Check list will contain the main sections to be reviewed, an Issue will be generated as items are added to the list.

The goal is to make the New ISO system invisible as a system to the users. In so far as the system is to enable the users to perform their function and not be an obsticle to the work flow.

Checklist of work to be carried out.

ISSUE ID	Summary	Thoughts	Completed
N/A	Create new Issue headers specifically / for Upgrading to the newer standards	New section has been added. / The section has also been linked to the management reviews and the board of directors meeting to ensure all upper management is aware and involved with the changes.	Yes.
66993	ISO Future TODO List	Issue log for this document
66989	Quality Policy objectives and policys
66990	Review the company flow charts	The current flow charts reflect of individual processes of the company link together / The new flowcharts should sart with the inputs of the Company and the outputs of the companys, breaking down into each section of the flow charts eventually leads to the actual procedures involved.
66991	Document System updates	The document system requires changes before we can start on the upgrade path. / A new data log need to be created for analysing risks relating to the documents.
66992	Issue system	The current issue system is the bedrock of the ISO system. / All management reviews, work flow reviews, customer complaints etc.. are hinged around the Issue system. / Current no changes are forseen however until the system upgrade is completed this cannot be guarenteed.

## Risks associated with this document.

There are no direct risks associated with this documents.
However the purpose on the document is to implement fundemental changes to the ISO system imployed by VIAMED / VST / VANDAGRAPH (to a limited degree) . So throughout the process the risk is we break / cause non conformances both in the final system and the system transition.

### Opportunities of the document.

The main opportunity is to reevaluate all processes within the system and make improvements along the way.

### Conclusion

The system upgrades are legally required so the risks have to be limited as best as possible.