VM3COP60.04
Viamed Disaster Planning
### Total Office/Warehouse Wipe out Plan
#### 1. Objectives
1. Relocate Offices
2. Relocate Warehouse
3. Restock Warehouse
4. Restore Office Functionality
5. Reactivate Computer Systems (Warehouse and Offices)
6. Restore Financial Systems

#### 2. Risk Assessment
Potential risks that could lead to a disaster:
- Natural disasters (e.g., fire, flood, extreme weather).
- Cyberattacks or data breaches.
- Power outages or utility failures.
- Equipment or infrastructure failure.
- Loss of key personnel.

#### 3. Response Timeline
Immediate Actions (0–4 hours):
- Redirect telephone systems.
- Establish temporary office and warehouse locations.
- Begin restoration of critical computer systems.
Short-Term (0–24 hours):
- Restore office functionality.
- Confirm communication continuity (email, phone).
- Notify key stakeholders of the situation.
Medium-Term (1–3 days):
- Start warehouse restocking.
- Notify customers of order backlog and provide recovery options.
- Ensure financial systems are operational.

#### 4. System Overview
- Modern Systems:
  The current system relies on Intrastats and Xero, which are fully browser-based and enable remote operations.
- Backup Readiness:
  - The old systems Opera and Goldmine are retained for historical data only.
  - Intrastats backups are live and maintained at a separate location, auto-updating daily.
- Continuity of Operations:
  - Remote work setups have proven effective, with minimal in-office staff required.
  - Communications are supported by a web-based phone system for uninterrupted customer service.

#### 5. Responsibilities
- Find new offices and redirect telephone systems: Helen Lamb
- Find new warehouse and redirect telephone systems: Helen Lamb
- Restock warehouse and notify suppliers: Steve Nixon
- Restore office functionality: Derek Lamb
- Restore computer systems (Warehouse and Offices): Derek Lamb
- Oversee financial systems and planning: Helen Lamb / Derek Lamb
- Manage insurance claims: Derek Lamb / Helen Lamb

#### 6. Dependencies and Constraints
- Dependencies:
  - Reliable internet and power supply.
  - Access to suppliers and external services (e.g., telecom providers).
  - Availability of backup hardware.
- Constraints:
  - Limited on-site staff for immediate response.
  - Lead time for suppliers to fulfil restocking.
  - Potential delays due to external factors (e.g., road closures, service provider capacity).

#### 7. Contact Information
- Telecom and Internet Provider: Firstcom Europe Ltd 0333 023 7000
- Key Suppliers: Honeywell, Bluepoint, Teledyne, Maxtec, Tidi, RS Components, Stationary and Packaging Companies.
- Insurance Provider: Thomas Sagar Insurances Ltd – Brown and Brown. nbaxter@sagarinsurances.co.uk www.sagarinsurances.co.uk

#### 8. Training and Drills
- Disaster recovery drills are conducted bi-annually to ensure readiness.
- All staff receive training on their specific responsibilities within the disaster recovery plan.

#### 9. Post-Recovery Actions
- Conduct a post-recovery review to identify lessons learned.
- Update this disaster recovery plan based on findings.
- Communicate the success of recovery efforts to stakeholders.
- Test backup systems to confirm data integrity.

#### 10. Data Protection Compliance
- All systems comply with GDPR requirements to ensure data confidentiality during recovery.
- Backup systems are encrypted and stored in secure locations.

#### 11. Key Performance Indicators (KPIs)
- Time taken to restore critical systems.
- Percentage of customers notified within 48 hours of system restoration.
- Percentage of systems operational within 4 hours of initiating recovery.

#### 12. Document Control
- Version: 3.0
- Date: [Insert Date]
- Approved By: [Insert Approver Name]

### Conclusions
Viamed has a robust disaster recovery plan that ensures:
- Rapid Recovery: Key systems restored in under 4 hours.
- Minimal Disruption: Remote work capabilities and browser-based tools minimize downtime.
- Customer Focus: Timely communication ensures customer satisfaction.