## Totals-Summary
Company Name: | Note: Do not enter data on this page except for cells A2, A4, A21, A23, A25 & A27. Enter all remaining data into the 'red-tabbed' sheets which follow. That data will be automatically captured on this sheet as an overall summary.
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised |  |  | Variance | Variance % | Notes
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total
Project Costs
Labour Costs | 11580 | 11580 | 23160 | 11580 | 11580 | 23160 | 0 | 0
Materials Costs | 1032 | 2256 | 3288 | 1032 | 3294.28 | 4326.25 | -1038.25 | -31.5769
Capital Equipment Costs | 0 | 5520 | 5520 | 0 | 950 | 950 | 4570 | 82.7899
Sub-Contract Costs | 29355 | 29355 | 58710 | 29355 | 29355 | 58710 | 0 | 0
Travel & Subsistence Costs | 1020 | 750 | 1770 | 595.39 | 644.38 | 1239.77 | 530.23 | 29.9565
Overhead Costs (postage, carriage, sundries, etc) | 0 | 0 | 0 | 0 | 40 | 40 | -40 | #DIV/0!
Other Costs | 600 | 270 | 870 | 845 | 75 | 920 | -50 | -5.7471
Total Project Costs | 43587 | 49731 | 93318 | 43407.39 | 45938.66 | 89346.02 | 3971.98 | 4.2564
Approved by Financial Controller or Accountant:
Signature_____________________
Derek Lamb
Viamed Ltd.
2017-07-05

## Labour Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  |  | Actual/Revised
| Hourly Cost | Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Labour Costs (Identity of each listed below)
Steve Nixon | 58.85 | 6120 | 6120 | 12240 | 6120 | 6120 | 12240 | 0 | 0
John Lamb | 58.85 | 3060 | 3060 | 6120 | 3060 | 3060 | 6120 | 0 | 0
Jan-Philip Bruening | 24.6 | 2400 | 2400 | 4800 | 2400 | 2400 | 4800 | 0 | 0
Manager/Staff 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Labour Costs |  | 11580 | 11580 | 23160 | 11580 | 11580 | 23160 | 0 | 0

## Materials Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Material Costs (Identity of each listed below)
Data capture electronics | 1032 | 0 | 1032 | 1032 | 0 | 1032 | 0 | 0
Specialist parts for sensors | 0 | 1440 | 1440 | 0 | 1440 | 1440 | 0 | 0
Moulding processing costs | 0 | 816 | 816 | 0 | 816 | 816 | 0 | 0
Battery for RAD-7 | 0 | 0 | 0 | 0 | 90.62 | 90.62 | -90.62 | #DIV/0! | EUR 102.99, for power back up & patient safety
RTC battery for RAD-7 | 0 | 0 | 0 | 0 | 3 | 3.49 | -3.49 | #DIV/0! | To synchronize patient data
SD cards (x11) | 0 | 0 | 0 | 0 | 79.66 | 79.66 | -79.66 | #DIV/0! | For datalogger patient data storage
Masimo disposable sensors | 0 | 0 | 0 | 0 | 194 | 193.68 | -193.68 | #DIV/0! | Supplied by Sheffield Children's Hospital for Gold standard reference
Parts for prototype sensors | 0 | 0 | 0 | 0 | 671 | 670.8 | -670.8 | #DIV/0! | 50 development sensors with Hydrogel/Neotech interface
Total Material Costs | 1032 | 2256 | 3288 | 1032 | 3294.28 | 4326.25 | -1038.25 | -31.5769

## Capital Equipment
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Capital Equipment Costs (Identity of each below)
Sensor prototype tooling/CAD drawing generation | 0 | 5520 | 5520 | 0 | 0 | 0 | 5520 | 100 | Not used, as focus group directed towards deveopment of new type of disposable sensors with innovative patient interface
Production of CAD drawings for oximeter concept design | 0 | 0 | 0 | 0 | 950 | 950 | -950 | #DIV/0! | To be presented at Phase II interview
Item 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Capital Equipment Costs | 0 | 5520 | 5520 | 0 | 950 | 950 | 4570 | 82.7899

## Sub-Contract Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Sub-Contract Costs (Identity of each below)
Professor Heather Elphick - SCH | 5793 | 5793 | 11586 | 5793 | 5793 | 11586 | 0 | 0
Dr Ruth Kingshott -SCH | 3300 | 3300 | 6600 | 3300 | 3300 | 6600 | 0 | 0
Dr Patrick Trotter - Medilink | 10842 | 10842 | 21684 | 10842 | 10842 | 21684 | 0 | 0
Tom Wright - Medilink | 6600 | 6600 | 13200 | 6600 | 6600 | 13200 | 0 | 0
Fadi Juniad - NIRI | 2820 | 2820 | 5640 | 2820 | 2820 | 5640 | 0 | 0
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Sub-Contract Costs | 29355 | 29355 | 58710 | 29355 | 29355 | 58710 | 0 | 0

## Travel & Subsistence
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Travel & Subsistence Costs (Identity of each below)
Travel | 570 | 570 | 1140 | 491.91 | 558.9 | 1050.81 | 89.19 | 7.8237
Subsistence | 180 | 180 | 360 | 103.48 | 85.48 | 188.96 | 171.04 | 47.5111
Travel - Focus Group | 270 | 0 | 270 | 0 | 0 | 0 | 270 | 100 | Unused, not wanted by the focus group.
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Travel & Subsistence Costs | 1020 | 750 | 1770 | 595.39 | 644.38 | 1239.77 | 530.23 | 29.9565

## Overhead Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Overhead Costs (Identity of each below)
Postage | 0 | 0 | 0 | 0 | 40 | 40 | -40 | #DIV/0! | UPS costs, 5 packages for SD cards with patient data
Carriage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sundries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Overhead Costs | 0 | 0 | 0 | 0 | 40 | 40 | -40 | #DIV/0!

## Other Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
"Other" Costs (including IP) (Itemisation of each below)
Research governance | 600 | 0 | 600 | 660 | 0 | 660 | -60 | -10
NHS IP support | 0 | 270 | 270 | 0 | 0 | 0 | 270 | 100 | No cost incurred
Focus group attendance costs | 0 | 0 | 0 | 105 | 75 | 180 | -180 | #DIV/0!
Focus group lunch costs | 0 | 0 | 0 | 80 | 0 | 80 | -80 | #DIV/0! | Not budgeted in the application, but offset against no travel costs.
Item 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total 'Other' Costs | 600 | 270 | 870 | 845 | 75 | 920 | -50 | -5.7471