| Activity and progress dashboard: Summary of Gantt chart (version 2 prepared 9/1/17) To be used at monitoring meetings. |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Activity | Owner | Target date | Comments |
|  | Benchmarking (clinical testing) of existing algorithm |  |  |  |
|  | Design of first phase clinical | SHC | 12/1/17 |  |
|  | Submission of ethics | SHC | 12/1/17 |  |
|  | Ethics approval meeting | SCH | 26/1/17 |  |
|  | Revisions and final approval | SCH | 22/3/17 |  |
|  | Architecture for data collection (equipment and SD card) documentation | SCH/Viamed | 11/1/17 |  |
|  | MEMG submission/meeting | SCH | 11/1/17 |  |
|  | Supply of equipment for clinical | Viamed | 1/2/17 |  |
|  | Initiation of phase I clinical |  |  |  |
|  | Clinical testing of algorithm | SCH | 31/5/17 |  |
|  | Report preparation on clinical testing | SCH | 14/6/14 |  |
|  | Clinical report and implications for phase II | SCH | 14/6/14 (milestone) |  |
|  | Scale of the problem |  |  |  |
|  | Inappropriate referrals from GPs | SCH | 28/2/17 |  |
|  | Benchmarking existing pathway | SCH |  |  |
|  | Competitor analysis |  |  |  |
|  | Competitor and IP analysis | Medilink | 10/2/17 |  |
|  | Competitor report preparation | Medilink | 24/2/17 |  |
|  | Clinical focus group |  |  |  |
|  | Design of questionnaire | Medilink | 23/1/17 |  |
|  | Presentation preparation | Medilink | 13/2/17 |  |
|  | Invitations to clinicians | SCH | 16/1/17 |  |
|  | Clinical workshop | Medilink/SCH | 28/2/17 |  |
|  | Clinical workshop report | Medilink | 13/3/17 |  |
|  | Patient focus group |  |  |  |
|  | Design of the questionnaire | Medilink | 15/2/17 |  |
|  | Presentation preparation | Medilink | 1/3/17 |  |
|  | Invitations to patient | SCH | 3/2/17 |  |
|  | Patient workshop | Medilink/ SCH | 9/3/17 |  |
|  | Patient needs report | Medilink | 14/3/17 |  |
|  | Idea generation |  |  |  |
|  | Idea generation |  | 15/3/17 |  |
|  | Idea generation/ concept enrichment |  | 12/4/17 |  |
|  | Concept prioritisation-Pugh matrix activity | All | 13/4/17 |  |
|  | Prioritised concepts (top 3-4) |  | Milestone |  |
|  | Soft prototyping and /or drawings |  | 18/5/17 |  |
|  | Validation focus group |  |  |  |
|  | Design of questionnaire and presentation | Medilink | 11/5/17 |  |
|  | Invitation of attendees | SCH | 20//3/17 |  |
|  | Validation focus group | Medilink | Week of 11/5/17 |  |
|  | Validation final concept report | Medilink | 15.5.17 |  |
|  | Initiation of prototyping selected concept | Viamed | Ongoing into phase II |  |
|  | Regulatory (CE marking & classification) | Viamed | 8/6/17 |  |
|  | IP strategy | Viamed | 8/617 |  |
|  | Final report and application for phase II |  |  |  |
|  | Final report preparation and plan for phase II |  | 26/6/17 |  |
|  | Final report submission |  | 26.76/17 |  |