# SBRI Healthcare: Oxygen monitoring management meeting 2

## Location

Room C3, Stephenson’s wing Sheffield Children's NHS Foundation Trust, Western Bank, Sheffield. S10 2TH

## Date and Time

9:30am-3pm, 24th January 2017

Summarised actions (previous meeting)

- ACTION – HE & RK to get SCH NDA signed and scanned across to SN & PT

- ACTION – RK to find out how often do the sensor probes get changed at SCH – feed back to SN

- ACTION – SN, HE and RK to use the Rad 7 as a ‘gold standard’ for the clinical testing in ethics

- ACTION – ALL to cc Medilink into all communications for auditing purposes

- ACTION – HE & RK - Will need to obtain ethics for at the earliest opportunity

- ACTION – ALL Review IP Strategy at every meeting based on project progress

- ACTION – PT & TW to include items discussed in management meeting 1 in the risk register within the project management folder

- ACTION – ALL agreed on management meeting followed by operational meeting to separate two activities

- ACTION – ALL determine dates for next meetings

  - Meeting 2 – just after Christmas on a Tuesday to attend the clinic – decide on 10th or 24th January

- ACTION – TW to send around meeting requests for dates for the remaining 5 management meetings

- ACTION – SN to ask Joop when we need to register our interest in Phase II

## Agenda

| No. | Item | Leader | Time |
| --- | --- | --- | --- |
|  | Heather Elphick Clinic Visit | HE |  |
|  | All to accompany HE on clinic visit. 9am meet in Stephenson Wing |  |  |
|  | Review of actions from previous meeting | All | 10 min |
|  | Matters arising | All | 15 min |
|  | Finance and invoicing arrangements | SN, PT | 10 min |
|  | Review project tracker – activities vs. milestones | All | 60 min |
|  | SBRI reporting requirements | SN, PT | 10 min |
|  | Any other business | All | 15 min |
|  | Date of next meeting (confirm) | All | 5 min |

Circulation:

Steve Nixon (SN)

Ruth Kingshott (RK)

Heather Elphick (HE)

Fadi Junaid (FJ)

Tom Wright (TW)

Patrick Trotter (PT