| Activity and progress dashboard: Summary of Gantt chart (version 2 prepared 9/1/17) To be used at monitoring meetings. |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Activity | Owner | Target date | Comments |
|  | Benchmarking (clinical testing) of existing algorithm |  |  |  |
|  | Design of first phase clinical | SHC | 12/1/17 |  |
|  | Submission of ethics | SHC | 12/1/17 |  |
|  | Ethics approval meeting | SCH | 26/1/17 |  |
|  | Revisions and final approval | SCH | 22/3/17 |  |
|  | Architecture for data collection (equipment and SD card) documentation | SCH/Viamed | 11/1/17 |  |
|  | MEMG submission/meeting | SCH | 11/1/17 |  |
|  | Supply of equipment for clinical | Viamed | 1/2/17 |  |
|  | Initiation of phase I clinical |  |  |  |
|  | Clinical testing of algorithm | SCH | 31/5/17 |  |
|  | Report preparation on clinical testing | SCH | 14/6/14 |  |
|  | Clinical report and implications for phase II | SCH | 14/6/14 (milestone) |  |
|  | Scale of the problem |  |  |  |
|  | Inappropriate referrals from GPs | SCH | 28/2/17 |  |
|  | Benchmarking existing pathway | SCH |  |  |
|  | Competitor analysis |  |  |  |
|  | Competitor and IP analysis | Medilink | 10/2/17 |  |
|  | Competitor report preparation | Medilink | 24/2/17 |  |
|  | Clinical focus group |  |  |  |
|  | Design of questionnaire | Medilink | 23/1/17 |  |
|  | Presentation preparation | Medilink | 13/2/17 |  |
|  | Invitations to clinicians | SCH | 16/1/17 |  |
|  | Clinical workshop | Medilink/SCH | 28/2/17 |  |
|  | Clinical workshop report | Medilink | 13/3/17 |  |
|  | Patient focus group |  |  |  |
|  | Design of the questionnaire | Medilink | 15/2/17 |  |
|  | Presentation preparation | Medilink | 1/3/17 |  |
|  | Invitations to patient | SCH | 3/2/17 |  |
|  | Patient workshop | Medilink/ SCH | 9/3/17 |  |
|  | Patient needs report | Medilink | 14/3/17 |  |
|  | Idea generation |  |  |  |
|  | Idea generation |  | 15/3/17 |  |
|  | Idea generation/ concept enrichment |  | 12/4/17 |  |
|  | Concept prioritisation-Pugh matrix activity | All | 13/4/17 |  |
|  | Prioritised concepts (top 3-4) |  | Milestone |  |
|  | Soft prototyping and /or drawings |  | 18/5/17 |  |
|  | Validation focus group |  |  |  |
|  | Design of questionnaire and presentation | Medilink | 11/5/17 |  |
|  | Invitation of attendees | SCH | 20//3/17 |  |
|  | Validation focus group | Medilink | Week of 11/5/17 |  |
|  | Validation final concept report | Medilink | 15.5.17 |  |
|  | Initiation of prototyping selected concept | Viamed | Ongoing into phase II |  |
|  | Regulatory (CE marking & classification) | Viamed | 8/6/17 |  |
|  | IP strategy | Viamed | 8/6/17 |  |
|  | Interim SBRI report | All | 22/3/17 | Five working days after Q1 (15th march) |
|  | Final report | All | 6th July2017 | 14 days after end of project |
|  | Submission for phase II | All | 6 July 2017 |  |

Milestones and key test for Phase 1 as set out in Schedule 1 of the SBRI Healthcare contract.

| # | Milestone | Date | Resource | Success Criteria |
| --- | --- | --- | --- | --- |
| 1 | Benchmark existing pathways | End of month 1 22nd Jan 2017 | Dr Ruth Kingshott and Prof Heather Elphick | Definition of current best practice. This provides the benchmark that the solution needs to surpass and also determine whether the value proposition should be in line with the technology fitting in with an existing pathway or a new one. |
| 2 | Focus groups 1,2 and 3 | 16 weeks 22 April 2017 | Ruth Kingshott and Heather Elphick toend users. Medilink to lead workshop and questionnaire design (with input from all) | Identification and prioritisation of user needs to convert to design inputs to link into product design. Identification of clinical evidence that will be required to be collected during phase II. |
| 3 | Competitor analysis and IP assessment | 8 weeks 22nd Feb 2017 | Medilink. An external law firm (HGF) will validate the assessment and manage future IP filings (phase II). | Assessment of freedom to operate and gaps/opportunities to file new IP. The exercise will also identify key threats and potentially opportunities. Clarity on route to market |
| 4 | NHS Ethics approval | 16 weeks 22nd April 2017 | Prof Heather Elphick and Dr Ruth Kingshott | Permission to conduct clinical evaluation during phase II. |
| 5 | Conversion of user needs to design inputs | 16 weeks 22nd April 2017 | All. The focus groups will play a key role in defining criteria and using inputs to refine product designs | A report that lists design inputs that are critical to quality (and linked to the end user needs). These design inputs will feed into the definition of the final product design. |
| 6 | Enrichment of concept | 20 weeks 22nd May 2017 | All including the Non Woven Research Institute (who will be contracted to aid in the final design and prototyping stages). | The definition of 3- 4 alternative designs and benchmarking with market leader (using Pugh matrix). Success criteria is definition of alternative product designs |
| 7 | Clinical study protocol | 24 weeks 22nd June | Prof Heather Elphick and Dr Ruth Kingshott | Formal clinical protocol to be used for clinical evaluation work |
| 8 | Equipment and NHS ethics approval for benchmark testing of existing devices | 8 weeks 22nd fenruary |  |  |
| 9 | Testing existing algorithms and products on 10 patients | 16 weeks 22nd April 2017 | Dr Ruth Kingshott and Prof Heather Elphick | It is important to benchmark the suitability of existing algorithms to identify and design the algorithm used in the clinical testing for phase II. |
| 10 | Selection & validation of concept to move into clinical testing (phase II) | 22nd June 2017 |  | . A final design spec and detailed product design will be the measure of success. |

Key Test:

A final design spec and detailed product design will be the measure of success.