# SBRI Healthcare: Oxygen monitoring management meeting 3

## Location

Medilink Yorkshire & Humber Ltd, 3, Smithy Wood Drive, Smithy Wood Business Park, Chapeltown, Sheffield, S35 1QN

## Date and Time

10am-1pm, 10th February 2017

Summarised actions (previous meeting)

- ACTION – TW put meeting request out for an internal concept selection meeting after meeting of 26th April (additional 2 hours – meeting lasting until 3pm)

- ACTION – TW share the clinical focus group protocol with the group at next meeting

- ACTION – HE to send contact details of the Leeds & Barnsley clinicians (& Lee Richardson – nurse for ventilated patients) to TW & contact details for Julia (retired nurse)

- ACTION – TW to let RK know which lunch we want to order for the focus group

- ACTION – HE to approach a small number of parent/patients to get people signed up to the patient focus group for PT & TW

- ACTION – SN create spreadsheet for finance, showing total paid to each subcontractor per month

- ACTION – SN to send a format for itemising costs to all partners so invoices are standardised

- ACTION – ALL partners to invoice Viamed quarterly – Prepare costs for end of March, including the correct customer name for each organisation

- ACTION – TW & PT define a date for the validation focus group BEFORE clinical focus group takes place

- ACTION – RK to take a look through methodologies for collecting clinical data relating to patient & carer anxiety when managing long term conditions – feeding into Phase II application

- ACTION – PT begin filling in the Interim Report, then send round to ALL partners for feedback

## Agenda

| No. | Item | Leader | Time |
| --- | --- | --- | --- |
|  | Review of actions from previous meeting | All | 10 min |
|  | Matters arising | All | 10 min |
|  | Finance and invoicing arrangements | SN, PT | 10 min |
|  | Review project tracker – activities vs. milestones | All | 60 min |
|  | Clinical interview questionnaire protocol | TW, PT | 20 min |
|  | Any other business | All | 10 min |
|  | Date of next meeting (confirm) | All | 5 min |

Circulation:

Steve Nixon (SN)

Ruth Kingshott (RK)

Heather Elphick (HE)

Fadi Junaid (FJ)

Tom Wright (TW)

Patrick Trotter (PT