# SBRI Healthcare: Oxygen monitoring management meeting 3

## Location

Medilink Yorkshire & Humber Ltd, 3, Smithy Wood Drive, Smithy Wood Business Park, Chapeltown, Sheffield, S35 1QN

## Date and Time

10am-1pm, 10th February 2017

Summarised actions (from this meeting)

- ACTION – PT & TW to put together presentation demonstrating results of the focus group & clinical interviews at next meeting to highlight findings for the technical team to follow up on.

- ACTION – RK to keep a record of sleep study patient records for the data contained within them – useful for identifying needs

- ACTION – HE to approach a small number of parent/patients to get people signed up to the patient focus group for PT & TW

- ACTION – TW & PT define a date for the validation focus group BEFORE clinical focus group takes place

- ACTION – TW & PT design two sessions (one for clinicians, one for patients) for the concept selection focus group to run individually

- ACTION – RK to book the CRF room 1-3pm for the patient concept selection session on Thursday 11th May. Other room is being booked by others within the hospital for the CPD

- ACTION – PT begin filling in the Interim Report, then send round to ALL partners for feedback

- ACTION – PT & TW to put interim report on the Agenda for next meeting for us all to go through together

- ACTION – SN, HE and RK to monitor Ethics Submission and report on progress at next meeting.

- ACTION – SN to do quarterly submissions for finance via PO number raised at Viamed. 2 payments to each partner at month 3 and month 6. Partners to itemise the bill for Viamed – Travel Expenses, Lunches, Mileage, Other costs (focus groups) etc.

Summarised actions (previous meeting)

- ACTION – TW put meeting request out for an internal concept selection meeting after meeting of 26th April (additional 2 hours – meeting lasting until 3pm)

- ACTION – TW share the clinical focus group protocol with the group at next meeting

- ACTION – HE to send contact details of the Leeds & Barnsley clinicians (& Lee Richardson – nurse for ventilated patients) to TW & contact details for Julia (retired nurse)

- ACTION – TW to let RK know which lunch we want to order for the focus group

- ACTION – HE to approach a small number of parent/patients to get people signed up to the patient focus group for PT & TW

- ACTION – SN create spreadsheet for finance, showing total paid to each subcontractor per month

- ACTION – SN to send a format for itemising costs to all partners so invoices are standardised

- ACTION – ALL partners to invoice Viamed quarterly – Prepare costs for end of March, including the correct customer name for each organisation

- ACTION – TW & PT define a date for the validation focus group BEFORE clinical focus group takes place

- ACTION – RK to take a look through methodologies for collecting clinical data relating to patient & carer anxiety when managing long term conditions – feeding into Phase II application

  - Self-care and monitoring at home – really drives this agenda

  - Might be worth putting these methodologies into Phase II project plan when designing a usability and human factors assessment – need to assess the home monitoring capabilities of the parents

- ACTION – PT begin filling in the Interim Report, then send round to ALL partners for feedback

## Agenda

| No. | Item | Leader | Time |
| --- | --- | --- | --- |
|  | Review of actions from previous meeting | All | 10 min |
|  | Matters arising – discussion of several items | All | 10 min |
|  | Project Scope Discussion regarding approach in Phase I vs. Phase II. PT stressed the importance of following a robust research process and aim for a more radical project. SN questioned whether it might be possible to deliver a quicker/simpler solution in the shorter term, and look at something more radical in the medium to long term? Agreed it could be a combination approach – deliver something quickly but aim for something more radical long term over Phase II. The market research with clinicians will help to validate our assumptions. Agreed amongst the group that we do not want a “fuzzy back end” to the project – need to be clear on the needs to feed into the design inputs. Need to make sure we are clear on what we want to develop. ACTION – PT & TW to put together presentation demonstrating results of the focus group & clinical interviews at next meeting to highlight findings for the technical team to follow up on. Patient Cohort HE talked about the patient cohort, and who we should be developing for: There are a large numbers of asthma patients, but these are cheaper to care for per head There are a smaller number of chronically ill respiratory patients, but these are more expensive to care for per head. Anonymised Sleep Study Records & Research approaches for assessing patient’s ability to self-care All agreed that the anonymised sleep study records collected by RK were extremely valuable in identifying needs ACTION – RK to keep a record of sleep study patient records for the data contained within them – useful for identifying needs RK papers very useful for understanding how we can assess usability and safety for self-care in home for a new device. There are techniques for collecting this research which we can learn from. Patient (2nd) Focus Group ACTION – HE to approach a small number of parent/patients to get people signed up to the patient focus group for PT & TW - HE mentioned that inpatients and parents of inpatients could be approached nearer the time to bring them in - HE and RK also pointed out that outpatients may be difficult to get hold of – they often live far away. We can potentially look at interviewing the patients instead – over the phone? They are good advocates so would be worthwhile approaching Concept Selection (3rd)Focus Group Reviewed the plan for the 3rd focus group – set date for Thursday 11th May when clinical CPD is also taking place. ACTION – TW & PT define a date for the validation focus group BEFORE clinical focus group takes place - HE look to book the session to tie in with a CPD session to get as many clinicians in the same room as possible ACTION – TW & PT design two sessions (one for clinicians, one for patients) for the concept selection focus group to run individually - Limit session to no more than an hour for each group – purely selection - Put a buffer amount of time in between the two – collate all the notes and write some of it up - Do the patient one in the afternoon – 13:30 to start well before school pick-up (parents of young children and older children who can advocate for themselves) - Thursday 11th May 10:30am for the clinical focus group (blocked out admin time) - Might get them for 30 mins to an hour ACTION – RK to book the CRF room 1-3pm for the patient concept selection session on Thursday 11th May. Other room is being booked by others within the hospital for the CPD SBRI Healthcare Interim Report ACTION – PT begin filling in the Interim Report, then send round to ALL partners for feedback - Going to bring this to the next meeting and go through it together. ACTION – PT & TW to put interim report on the Agenda for next meeting for us all to go through together |  |  |
|  | Ethics submission & contract | HE, SN | 10 min |
|  | Submission goes to ethics, then HRA (Health Research Authority) then to local R&D board. Can’t do the local sign off with the R&D board until they receive the contracts. Device is not the problem – it’s that we need to include patients in the study. It is research (even with anonymous data) we are collecting data which we will be analysing. Phase II is easier generally speaking. Materials – have they been used on children/skin before? When NIRI and Viamed are doing R&D work they need to make sure the materials are safe for use and have a known and quantified benefit. Viamed have an indemnity insurance for the NHS which should allow them straight into Medical Physics. ACTION – SN, HE and RK to monitor this and report on progress at next meeting. |  |  |
|  | Finance and invoicing arrangements | SN, PT | 10 min |
|  | SN suggested quarterly bills for costs ACTION – SN to do quarterly submissions for finance via PO number raised at Viamed. 2 payments to each partner at month 3 and month 6. Partners to itemise the bill for Viamed – Travel Expenses, Lunches, Mileage, Other costs (focus groups) etc. |  |  |
|  | Review project tracker – activities vs. milestones | All | 60 min |
|  | Discussion regarding Patrick’s competitor’s report. Discussion regarding patent law and strategies for patenting a future device. |  |  |
|  | Sensor fixation methods | SN | 20 min |
|  | SN reviewed the current range of sensors: - 4 different products – neonate, infant, young child and adult - Samples of products to look at bringing to the focus group - Two things Steve thinks we could look at: - Securing the optics in place - Securing the entire probe together - Hydrocolloid gel/hydrogel could take the ‘rock’ away from the optics on the finger etc. - Optics are moving to 1mm 0.5mm size – very small - Could we look at a combination product? Wireless sensor is reusable but the interface is disposable - Line of sight for emitter and sensor – they can be put on a flat surface and reflect off the forehead for example back in at an acute angle, rather than straight through a digit in a straight line |  |  |
|  | Clinical interview questionnaire protocol | TW, PT | 20 min |
|  | Covered – several suggestions for adaptation of the questionnaire to ensure all areas are covered |  |  |
|  | Any other business | All | 10 min |
|  | Date of next meeting (confirm) | All | 5 min |

Circulation:

| Steve Nixon (SN) | Heather Elphick (HE) | Fadi Junaid (FJ) |
| --- | --- | --- |
| Ruth Kingshott (RK) | Patrick Trotter (PT | Tom Wright (TW) |