# SBRI Healthcare: Oxygen monitoring management meeting 4

## Location

Nonwovens Innovation & Research Institute Ltd, Clothworkers' Building Central, University of Leeds, Woodhouse Lane, Leeds LS2 9JT

## Date and Time

10am-3pm, 15th March 2017

Summarised actions (previous meeting)

- ACTION – PT & TW to put together presentation demonstrating results of the focus group & clinical interviews at next meeting to highlight findings for the technical team to follow up on.

- ACTION – RK to keep a record of sleep study patient records for the data contained within them – useful for identifying needs

- ACTION – HE to approach a small number of parent/patients to get people signed up to the patient focus group for PT & TW

- ACTION – TW & PT define a date for the validation focus group BEFORE clinical focus group takes place

- ACTION – TW & PT design two sessions (one for clinicians, one for patients) for the concept selection focus group to run individually

- ACTION – RK to book the CRF room 1-3pm for the patient concept selection session on Thursday 11th May. Other room is being booked by others within the hospital for the CPD

- ACTION – PT begin filling in the Interim Report, then send round to ALL partners for feedback

- ACTION – PT & TW to put interim report on the Agenda for next meeting for us all to go through together

- ACTION – SN, HE and RK to monitor Ethics Submission and report on progress at next meeting.

- ACTION – SN to do quarterly submissions for finance via PO number raised at Viamed. 2 payments to each partner at month 3 and month 6. Partners to itemise the bill for Viamed – Travel Expenses, Lunches, Mileage, Other costs (focus groups) etc.

## Agenda

| No. | Item | Leader | Time |
| --- | --- | --- | --- |
|  | Review of actions from previous meeting | All | 10 min |
|  | Matters arising | All | 10 min |
|  | Review project tracker – activities vs. milestones | All | 20 mins |
|  | Ethics submission & contract | HE, SN | 10 min |
|  | SBRI Interim Report | PT, SN | 20 mins |
|  | Finance and invoicing arrangements | SN, PT | 10 min |
|  | Patient & Clinician research findings | TW, PT | 60 min |
|  | Any other business | All | 10 min |
|  | - TITCH event 27th April |  |  |
|  | Date of next meeting (confirm) | All | 5 min |

Circulation:

| Steve Nixon (SN) | Heather Elphick (HE) | Fadi Junaid (FJ) |
| --- | --- | --- |
| Ruth Kingshott (RK) | Patrick Trotter (PT | Tom Wright (TW) |