## Totals-Summary
Company Name: | Note: Do not enter data on this page except for cells A2, A4, A21, A23, A25 & A27. Enter all remaining data into the 'red-tabbed' sheets which follow. That data will be automatically captured on this sheet as an overall summary.
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised |  |  | Variance | Variance % | Notes
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total
Project Costs
Labour Costs | 11580 | 11580 | 23160 | 11580 | 0 | 11580 | 11580 | 50
Materials Costs | 1032 | 2256 | 3288 | 1032 | 0 | 1032 | 2256 | 68.6131
Capital Equipment Costs | 0 | 5520 | 5520 | 0 | 0 | 0 | 5520 | 100
Sub-Contract Costs | 29355 | 29355 | 58710 | 29355 | 0 | 29355 | 29355 | 50
Travel & Subsistence Costs | 1020 | 750 | 1770 | 0 | 0 | 0 | 1770 | 100
Overhead Costs (postage, carriage, sundries, etc) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other Costs | 1050 | 270 | 1320 | 1130 | 0 | 1130 | 190 | 14.3939
Total Project Costs | 44037 | 49731 | 93768 | 43097 | 0 | 43097 | 50671 | 54.0387
Approved by Financial Controller or Accountant:
Signature_____________________
Derek Lamb
Viamed Ltd.
2017-03-22

## Labour Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  |  | Actual/Revised
| Hourly Cost | Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Labour Costs (Identity of each listed below)
Steve Nixon | 58.85 | 6120 | 6120 | 12240 | 6120 | 0 | 6120 | 6120 | 50
John Lamb | 58.85 | 3060 | 3060 | 6120 | 3060 | 0 | 3060 | 3060 | 50
Jan-Philip Bruening | 24.6 | 2400 | 2400 | 4800 | 2400 | 0 | 2400 | 2400 | 50
Manager/Staff 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Manager/Staff 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Labour Costs |  | 11580 | 11580 | 23160 | 11580 | 0 | 11580 | 11580 | 50

## Materials Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Material Costs (Identity of each listed below)
Data capture electronics | 1032 | 0 | 1032 | 1032 | 0 | 1032 | 0 | 0 | May be revised, lower.
Specialist parts for sensors | 0 | 1440 | 1440 | 0 | 0 | 0 | 1440 | 100
Moulding processing costs | 0 | 816 | 816 | 0 | 0 | 0 | 816 | 100
Item 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Material Costs | 1032 | 2256 | 3288 | 1032 | 0 | 1032 | 2256 | 68.6131

## Capital Equipment
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Capital Equipment Costs (Identity of each below)
Sensor prototype tooling/CAD drawing generation | 0 | 5520 | 5520 | 0 | 0 | 0 | 5520 | 100
Item 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Capital Equipment Costs | 0 | 5520 | 5520 | 0 | 0 | 0 | 5520 | 100

## Sub-Contract Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Sub-Contract Costs (Identity of each below)
Professor Heather Elphick - SCH | 5793 | 5793 | 11586 | 5793 | 0 | 5793 | 5793 | 50
Dr Ruth Kingshott -SCH | 3300 | 3300 | 6600 | 3300 | 0 | 3300 | 3300 | 50
Dr Patrick Trotter - Medilink | 10842 | 10842 | 21684 | 10842 | 0 | 10842 | 10842 | 50
Tom Wright - Medilink | 6600 | 6600 | 13200 | 6600 | 0 | 6600 | 6600 | 50
Fadi Juniad - NIRI | 2820 | 2820 | 5640 | 2820 | 0 | 2820 | 2820 | 50
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Sub-Contract Costs | 29355 | 29355 | 58710 | 29355 | 0 | 29355 | 29355 | 50

## Travel & Subsistence
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Travel & Subsistence Costs (Identity of each below)
Travel | 570 | 570 | 1140 | 0 | 0 | 0 | 1140 | 100 | Awaiting Q1 receipts
Subsistence | 180 | 180 | 360 | 0 | 0 | 0 | 360 | 100 | Awaiting Q1 receipts
Travel - Focus Group | 270 | 0 | 270 | 0 | 0 | 0 | 270 | 100 | Not used
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Travel & Subsistence Costs | 1020 | 750 | 1770 | 0 | 0 | 0 | 1770 | 100

## Overhead Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
Overhead Costs (Identity of each below)
Postage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Carriage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sundries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total Overhead Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!

## Other Costs
Company Name:
Viamed Ltd.
Project Title:
Portable wearable paediatric oxygen monitoring device | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT) |  |  | SBRI Healthcare Phase 1 Application (Costs inclusive of VAT)
| Budget (from contract) |  |  | Actual/Revised
| Qtr 1 | Qtr 2 | Total | Qtr 1 | Qtr 2 | Total | Variance | Variance % | Notes
Project Costs
"Other" Costs (including IP) (Itemisation of each below)
Research governance | 600 | 0 | 600 | 1050 | 0 | 1050 | -450 | -75
NHS IP support | 0 | 270 | 270 | 0 | 0 | 0 | 270 | 100 | To be processed in Q2
Focus group attendance costs | 450 | 0 | 450 | 0 | 0 | 0 | 450 | 100
Focus group lunch costs | 0 | 0 | 0 | 80 | 0 | 80 | -80 | #DIV/0! | Not budgeted in the application, but offset against no travel costs.
Item 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Item 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Total 'Other' Costs | 1050 | 270 | 1320 | 1130 | 0 | 1130 | 190 | 14.3939