| Activity and progress dashboard: Summary of Gantt chart (version 3 prepared 19/1/17) To be used at monitoring meetings. |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Activity | Owner | Target date | Comments |
|  | Benchmarking (clinical testing) of existing algorithm |  |  |  |
|  | Design of first phase clinical | SHC | 12/1/17 | Complete |
|  | Submission of ethics | SHC | 12/1/17 | Complete |
|  | Ethics approval meeting | SCH | 26/1/17 26/2/17 | Now just waiting to hear via email (likely we won’t need to go before panel). Will be pushed on a month. Complete |
|  | Revisions and final approval | SCH | 22/3/17 02/05/17 | Ethics are delayed by a potential clerical error at the HRA. Will be approved in early May. Ethics are valid until June 2017 at present. |
|  | Architecture for data collection (equipment and SD card) documentation | SCH/Viamed | 11/1/17 10/3/17 15/3/17 | Mid-March target for this task at the latest Steve is working on this at present. Tweaking a board and getting a PCB which is compliant for data collection. Needs to be able to collect data from the Masimo and the Viamed device. Electrical testing should be fine. Masimo electrical safety testing will be needed (battery and mains powered functions) but should not take long. Mid-March finish to align with the ethics approval. Could spend Phase II refining the user interface and data reporting. |
|  | MEMG submission/meeting | SCH | 11/1/17 08/2/17 | Complete |
|  | Supply of equipment for clinical | Viamed | 26/04/17 | Equipment handed to Medical Physics for testing and approval SN going to give the equipment to RK to bring to medical physics. Complete |
|  | Initiation of phase I clinical |  |  |  |
|  | Clinical testing of algorithm | SCH | 31/5/17 | Initial date was 31st May. Likely this will be pushed onto early June. Just need to have to Content of the final report: - Demographic data, user data (anonymised) - Feedback - Algorithm testing Delivery of study: - RK to go out to home monitoring patients with Julie Bell to collect measurements from this cohort - Collecting data from a range of ages Requirements - Put the probe onto the same limb and digit - Minimum of 30 mins recording on the target limb - Ruth – download the Masimo data in the Hospital (clinically) - Send the SD onto Steve for download. - Steve then sends this data back to Ruth so the comparison can be made |
|  | Report preparation on clinical testing | SCH | 14/6/14 | Mid-June start to get report together on the clinical testing and the results. |
|  | Clinical report and implications for phase II | SCH | 14/6/14 (milestone) | Final deadline for reporting on the outcome of the study in clinical terms |
|  | Scale of the problem |  |  |  |
|  | Inappropriate referrals from GPs | SCH | 28/2/17 | Question modified slightly – Reducing number phone calls, home visits, outpatient visits etc. Not necessarily the GP referral route where patients come from. Reducing cost of travel visiting home care patients in wider area. Rationale: When we delved deeper, we refocused the project on a more specific area which was judged to be more relevant as a clinical problem to be solved. This is justification for our modified approach. 15 departments like the SCH clinic in the UK – first target for the research. |
|  | Benchmarking existing pathway | SCH |  | See above. Parents will have stories which we could capture from the patient group e.g. “I really could have done with an oximeter when we were in the park that time, and we ended up rushing into the hospital” etc. Case studies for false positives and false negatives due to a lack of a decent oximeter. Asthma desaturation isn’t common, and it is so fast that an SPO2 measure wouldn’t necessarily be useful in the workflow. Respiratory patients there is a time lag with SPO2. Parents may have little oxygen and the child is in critical state – could be avoided. The risk level is so high and patient anxiety is so high that even a small amount of risk reduction would have a large positive impact on quality of life. |
|  | Competitor analysis |  |  |  |
|  | Competitor and IP analysis | Medilink | 10/2/17 | Complete |
|  | Competitor report preparation | Medilink | 24/2/17 | Complete |
|  | Clinical focus group |  |  |  |
|  | Design of questionnaire | Medilink | 23/1/17 | Complete |
|  | Presentation preparation | Medilink | 13/2/17 | Complete |
|  | Invitations to clinicians | SCH | 16/1/17 | Complete |
|  | Clinical workshop | Medilink/SCH | 28/2/17 | Complete |
|  | Clinical workshop report | Medilink | 13/3/17 | Complete |
|  | Patient focus group |  |  |  |
|  | Design of the questionnaire | Medilink | 15/2/17 | Complete |
|  | Presentation preparation | Medilink | 1/3/17 | Complete |
|  | Invitations to patient | SCH | 3/2/17 | Complete |
|  | Patient workshop | Medilink/ SCH | 9/3/17 | Complete |
|  | Patient needs report | Medilink | 14/3/17 | Complete |
|  | Idea generation |  |  |  |
|  | Idea generation |  | 15/3/17 Extended to 26/04/17 | Begun – 6 concepts generated so far for final focus group |
|  | Idea generation/ concept enrichment |  | 12/4/17 26/04/17 |  |
|  | Concept prioritisation-Pugh matrix activity | All | 13/4/17 26/05/17 |  |
|  | Prioritised concepts (top 3-4) |  | Milestone 26/04/17 |  |
|  | Soft prototyping and /or drawings |  | 18/5/17 |  |
|  | Validation focus group |  |  |  |
|  | Design of questionnaire and presentation | Medilink | 09/5/17 |  |
|  | Invitation of attendees | SCH/Medilink | 05/05/17 |  |
|  | Validation focus group | Medilink | 11/5/17 |  |
|  | Validation final concept report | Medilink | 17/5/17 |  |
|  | Initiation of prototyping selected concept | Viamed | Ongoing into phase II |  |
|  | Regulatory (CE marking & classification) | Viamed | 8/6/17 |  |
|  | IP strategy | Viamed | 8/6/17 |  |
|  | Interim SBRI report | All | 22/3/17 | Five working days after Q1 (15th march) |
|  | Final report | All | 6th July2017 | 14 days after end of project |
|  | Submission for phase II | All | 6 July 2017 |  |

Milestones and key test for Phase 1 as set out in Schedule 1 of the SBRI Healthcare contract.

| # | Milestone | Date | Resource | Success Criteria |
| --- | --- | --- | --- | --- |
| 1 | Benchmark existing pathways | End of month 1 22nd Jan 2017 | Dr Ruth Kingshott and Prof Heather Elphick | Definition of current best practice. This provides the benchmark that the solution needs to surpass and also determine whether the value proposition should be in line with the technology fitting in with an existing pathway or a new one. |
| 2 | Focus groups 1,2 and 3 | 16 weeks 22 April 2017 | Ruth Kingshott and Heather Elphick toend users. Medilink to lead workshop and questionnaire design (with input from all) | Identification and prioritisation of user needs to convert to design inputs to link into product design. Identification of clinical evidence that will be required to be collected during phase II. |
| 3 | Competitor analysis and IP assessment | 8 weeks 22nd Feb 2017 | Medilink. An external law firm (HGF) will validate the assessment and manage future IP filings (phase II). | Assessment of freedom to operate and gaps/opportunities to file new IP. The exercise will also identify key threats and potentially opportunities. Clarity on route to market |
| 4 | NHS Ethics approval | 16 weeks 22nd April 2017 | Prof Heather Elphick and Dr Ruth Kingshott | Permission to conduct clinical evaluation during phase II. |
| 5 | Conversion of user needs to design inputs | 16 weeks 22nd April 2017 | All. The focus groups will play a key role in defining criteria and using inputs to refine product designs | A report that lists design inputs that are critical to quality (and linked to the end user needs). These design inputs will feed into the definition of the final product design. |
| 6 | Enrichment of concept | 20 weeks 22nd May 2017 | All including the Non Woven Research Institute (who will be contracted to aid in the final design and prototyping stages). | The definition of 3- 4 alternative designs and benchmarking with market leader (using Pugh matrix). Success criteria is definition of alternative product designs |
| 7 | Clinical study protocol | 24 weeks 22nd June | Prof Heather Elphick and Dr Ruth Kingshott | Formal clinical protocol to be used for clinical evaluation work |
| 8 | Equipment and NHS ethics approval for benchmark testing of existing devices | 8 weeks 22nd fenruary |  |  |
| 9 | Testing existing algorithms and products on 10 patients | 16 weeks 22nd April 2017 | Dr Ruth Kingshott and Prof Heather Elphick | It is important to benchmark the suitability of existing algorithms to identify and design the algorithm used in the clinical testing for phase II. |
| 10 | Selection & validation of concept to move into clinical testing (phase II) | 22nd June 2017 |  | . A final design spec and detailed product design will be the measure of success. |

Key Test:

A final design spec and detailed product design will be the measure of success.